LandCare Day 1 Findings

Baseline QA readout | 2026-06-09

Database: gisdb  Connection: pgAdmin URA GISDB, user rutomo  Mode: Read-only inspection queries

Bottom line: The dashboard returned-survey count of 142 can be reproduced, but only after normalizing parcel keys and matching surveys back to assignment keys. The cleaner operating rate is Active-only completion at 14.0%.

# Insights

### The returned-survey count is reproducible, but only after parcel-key normalization.

Evidence: SQL has 149 current-quarter survey rows and 144 normalized survey keys. Of those, 142 match the assignment universe.

Meaning: The dashboard return count is defensible, but the reconciliation logic should be explicit. Unmatched survey keys need a small exception queue.

### The assignment denominator needs cleanup before dashboard or model changes.

Evidence: The same assignment universe shows 1,221 rows, 1,220 displayed parcel numbers, and 1,095 normalized parcel keys.

Meaning: Leadership should avoid treating the blended denominator as final until duplicate and formatting issues are resolved.

### Active-only completion is the cleaner operating metric.

Evidence: Active parcels show 142 returned assignment keys out of 1,011 assigned keys, or 14.0%. Request Only shows 0 out of 90.

Meaning: Active and Request Only should be reported separately. A blended rate makes field performance harder to interpret.

### Contractor performance is highly uneven.

Evidence: One Call is 89.5%, Ervin is 64.3%, and FHCV is 57.7%. KRJ is 1.1%, Chatman is 1.5%, and two Active groups are at 0.0%.

Meaning: The spread supports a targeted operations review. Compare high performers against low performers by route burden, assignment quality, and reporting behavior.

# Baseline Metrics

| Metric | Value |
| --- | --- |
| Assignment rows from gis.epp_snapshot | 1,221 |
| Distinct parcel_number values | 1,220 |
| Distinct normalized assignment keys | 1,095 |
| Current-quarter survey rows | 149 |
| Distinct current-quarter survey keys | 144 |
| Matched returned assignment keys | 142 |
| Unmatched returned survey keys | 2 |

# Operating Implications

Metric governance: standardize the parcel-key join before changing the dashboard or building a model.

Dashboard clarity: show Active-only completion beside the blended rate and keep Request Only separate.

Operations follow-up: review contractor outliers first. The spread is too large to treat as one Regrid issue.

Data quality: keep unmatched survey keys visible so returned work does not disappear during reconciliation.

# Recommended Next Actions

Adopt normalized parcel key logic for assignment and survey joins.

Add Active-only completion to the dashboard next to the blended rate.

Create an unmatched survey queue for the two current-quarter returned keys that do not map to assignments.

Run the ownership join next to flag sold or non-URA parcels before assignment.

Use contractor outliers to guide follow-up before investing in a model or Regrid replacement.

Attached data package: CSV exports from the Day 1 read-only PostgreSQL inspection are packaged separately as a ZIP file.